## Sheet1
Vincent Ho, Robbie Rao, Nanson Zheng, Kirisanth Ganeshamoorthy, Dimitar Stratiev |  | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-09 | 2015-11-10
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Task Sum
As Natalie, a Historian, I want to be able to rename all identical tags at once across all files and directories | Spike #1: Learn JavaScript | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Task #1: Create XUL files for installation of Zotero Extension | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Task #2: documentation of functions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task #3: Implement a function to search for all relevant items, given a list of tags | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5
| Task #4: Implement a function to delete a tag from all items containing the tag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task #5: Implement a function to add a tag to multiple items | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task #6: Implement a button on Zotero's default window for batch editing tags | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task #7: Incorporation of javascript and gui | 1 | 1 | 1 | 0.5 | 0 | 0 | 1.5 | 1 | 1 | 0.5 | 7.5
Daily Work Sum |  | 2 | 1 | 1 | 0.5 | 0 | 0 | 1.5 | 1 | 1 | 2 | 10
Total Work | 10