## Sheet1
Estimated
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Task Sum
As Natalie, a Historian, I want a checklist prompt to save changes across all identical files in all directories so my files are consistent | Spike #1: Learn Zotero System | 3.5 | 3.5 | 2.5 | 2.5 | 2 | 2 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 25
| Spike #2: Learn JavaScript | 3.5 | 3.5 | 2.5 | 2.5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 25
| Task #1: Create a simple text pop-up prompt | 0 | 0 | 1 | 1 | 1.5 | 1.5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 10
| Task #2: create a checklist in the pop-up prompt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 5
| Task #3: retrieve duplicate files for a specified file | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 2 | 2 | 2 | 2.5 | 2.5 | 2 | 2 | 2 | 20
| Task #4: implement file I/O | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
| Task #5: documentation of functions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
Daily Work Sum |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6
Total Work | 97
Actual | Vincent Ho: Red, Robbie Rao: Orange, Nanson Zheng: Green, Kirisanth Ganeshamoorthy Blue | Day 6: Dimitar Stratiev
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Task Sum
As Natalie, a Historian, I want a checklist prompt to save changes across all identical files in all directories so my files are consistent | Spike #1: Learn Zotero System | v: 2 | v: 2, K: 1 | R:2.5, K: 1 | v: 1 | R:2, V:2 | 0 | V: 1 | 0 | 0 | V: 1 | 0 | 0 | 0 | 0 | 15.5
| Spike #2: Learn JavaScript | v: 1 | v: 1 | K: 1 | v: 1 | K: 1 | N: 3 | 0 | K: 2 | K: 1 | N: 2 | 0 | 0 | 0 | K: 1 | 14
| Task #1: Create a simple text pop-up prompt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task #2: create a checklist in the pop-up prompt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | D: 2.5 | 2.5
| Task #3: retrieve duplicate tags for a specified file | 0 | 0 | 0 | 0 | 0 | 0 | K: 2 | K: 2 | K: 2 | 0 | K: 2.5 | 0 | 0 | K: 2 | 10.5
| Task #4: implement file I/O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task #5: documentation of functions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N: 5 | 5
Daily Work Sum |  | 3 | 4 | 4.5 | 2 | 5 | 3 | 3 | 4 | 3 | 3 | 2.5 | 0 | 0 | 10.5